## Gantt
30 DAY CLOSE
GANTT CHART
*Assumes a house bought from realtor.com with a private lender, assumes no counter-offers
| W1 | [6 empty] | W2 | [6 empty] | W3 | [6 empty] | W4 | [6 empty] | W5 | [6 empty] | W6
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37
Purchase and Sale signed | bar: W1 1
Inspection period | bar: W1 2 to W3 15
Seller to provide disclosure info | bar: W1 2 to W2 8
Title inspection | bar: W1 2 to W3 15
Earnest money transferred | bar: W1 2 to W2 12
Resolution period | bar: W3 16 to W3 19
Promissory note signed | bar: W3 19
Funds transferred into escrow | bar: W3 20 to W5 29
Property management arranged | bar: W3 20 to W5 29
Final inspection | bar: W4 28 to W5 29
Arrange insurance | bar: W4 25 to W5 29
Deed recorded | bar: W5 30 to W5 31
Deed of Trust registered | bar: W5 31 to W6 36
|  | purchaser | [6 empty] | third party | [5 empty] | coordinated by purchaser | [6 empty] | closing date
www.lotusglobalassets.com